## Status Update
No. | Project Name | Brief Description | Comments | Developer | Coordinator | Target Go-Live date | Status
1 | NUSmod | Timetabling application | Original onboarding | eliang@nusmods.com | eliang@nusmods.com | Nov 2019 | Completed migration to SDP production system
2 | KEVII Hall portal cum facility booking system | Hall portal cum facility booking system | Referred by Yen Teck | ziyun_yang@u.nus.edu zhida.teh@u.nus.edu | kehnha@nus.edu.sg | Beginning of next Sem | Students are currently developing application in SDP.
3 | Eusof Hall Portal | Hall portal | Referred by Eng Hee | NA | eshnjw@nus.edu.sg | NA | User currently has a PC that hosts financial data for student groups (eg amount of budget spent by the gardening group etc) They would like to upgrade this to a portal based system for easier access and increased robustness. Currently, they are organising their student IT team and that the portal is still in the design phase. They would contact us once they are ready with the development.
4 | Kent Ridge Hall KRMealBot | Telegram bot for feedback. Particularly for meals. | NUS Cloud | adrielngch@u.nus.edu | pvohgh@nus.edu.sg | Beginning of next Sem | Student granted access to SDP. In development stage?
5 | Recruitment System | Match jobseekers to jobs |  | Pereira Yip Ding Xian - E0175340 Tan Wei Shin Dalson - E0036924 Ng Hao Yuan - E0031554 Neo Kang Wei - E0031583 Jocelyn Tan Hui Lin - E0141639 | Neo Kang Wei - E0031583 | NA | Student granted access to SDP. In development stage?
6 | FAQ application | Answering FAQ with AI |  | jnew@u.nus.edu | jnew@u.nus.edu | NA | Student granted access to SDP. In development stage?